## Dashboard
RISK ASSESSMENT & RISK REGISTER
BrightPay Fintech ¦ ISO 27001:2022 Annex A ¦ 5×5 Likelihood-Impact Matrix ¦ 2025
10 | ~18 |  | ~10 |  | ~60% | 5
Risks Identified | Avg. Inherent Score |  | Avg. Residual Score |  | High-Risk Reduction | Controls Applied
Scope | Fintech SaaS — customer data, payment processing, cloud infrastructure, third-party APIs
Framework | ISO 27001:2022 Annex A ¦ 5×5 Risk Scoring Matrix
Asset Categories | Cloud Infrastructure · Payment APIs · User Data Stores · Admin Accounts · Third-Party Integrations · Employee Endpoints
Risk Owners | CISO · IT Manager · Compliance Lead · DevOps Lead
Review Cadence | Quarterly — High Risks ¦ Bi-annually — Medium / Low Risks
Scoring Thresholds | High ≥ 15 ¦ Medium 8–14 ¦ Low < 8 ¦ Max Score = 25 (5 × 5)
RISK TIER LEGEND
HIGH | Score >= 15 ¦ Immediate action ¦ Quarterly review | MEDIUM |  | Score 8-14 ¦ Controls required ¦ Bi-annual review | LOW |  | Score < 8 ¦ Monitor ¦ Annual review

## Risk Register
BrightPay Fintech — Risk Register ¦ ISO 27001:2022 Annex A ¦ 2025
|  |  |  | INHERENT RISK |  |  | CONTROL | RESIDUAL RISK
Risk ID | Asset Category | Risk Description | Threat Type | Likelihood (1–5) | Impact (1–5) | Inherent Score | Control Applied (Annex A Reference) | Likelihood (Post-Control) | Impact (Post-Control) | Residual Score | Risk Tier | Risk Owner | Next Review | Status
R-001 | Payment APIs | Unauthorised access to payment APIs via stolen or weak credentials | Credential Attack | 4 | 5 | 20 | MFA (A.8.5) + RBAC (A.8.2) + API Key Rotation | 2 | 4 | 8 | MEDIUM | CISO | Q3 2025 | Controls Implemented
R-002 | User Data Stores | Data breach via unencrypted data storage exposing customer PII | Data Exposure | 3 | 5 | 15 | AES-256 Encryption at Rest (A.8.24) + DLP | 2 | 3 | 6 | LOW | IT Manager | Q3 2025 | Controls Implemented
R-003 | Admin Accounts | Privilege escalation by malicious insider gaining unauthorised admin access | Insider Threat | 3 | 4 | 12 | RBAC (A.8.2) + Quarterly Access Review (A.8.3) | 2 | 3 | 6 | LOW | CISO | Q2 2025 | Review Scheduled
R-004 | Cloud Infrastructure | DDoS attack overwhelming payment gateway and causing service outage | Availability Attack | 4 | 4 | 16 | WAF + Rate Limiting (A.8.20) + Redundancy | 2 | 4 | 8 | MEDIUM | DevOps Lead | Q3 2025 | Controls Implemented
R-005 | Third-Party Integrations | Third-party API compromise propagating attack to BrightPay systems | Supply Chain Attack | 3 | 4 | 12 | Vendor Risk Assessment (A.5.19) + Contractual SLA | 2 | 4 | 8 | MEDIUM | Compliance Lead | Q3 2025 | Monitoring
R-006 | Employee Endpoints | Malware infection via phishing email on employee endpoint | Phishing / Malware | 4 | 3 | 12 | Endpoint Detection & Response (A.8.7) + Security Awareness Training (A.6.3) | 2 | 3 | 6 | LOW | IT Manager | Q2 2025 | Training Ongoing
R-007 | Cloud Infrastructure | Misconfigured cloud storage bucket exposing sensitive data publicly | Misconfiguration | 3 | 5 | 15 | Cloud Security Posture Mgmt (A.8.9) + Config Audit | 1 | 4 | 4 | LOW | DevOps Lead | Q2 2025 | Controls Implemented
R-008 | User Data Stores | SQL injection attack against customer database via web application | Injection Attack | 3 | 5 | 15 | WAF (A.8.20) + Input Validation + Penetration Testing (A.8.8) | 1 | 4 | 4 | LOW | IT Manager | Q3 2025 | Controls Implemented
R-009 | Admin Accounts | Shared or unrotated admin credentials enabling persistent unauthorised access | Credential Misuse | 3 | 4 | 12 | Password Policy (A.8.5) + Privileged Access Mgmt + Rotation Policy | 2 | 3 | 6 | LOW | IT Manager | Q2 2025 | Policy Published
R-010 | Third-Party Integrations | Inadequate due diligence on new third-party vendor introducing compliance risk | Compliance / Legal Risk | 2 | 4 | 8 | Vendor Onboarding Process (A.5.19) + SoA Review | 1 | 3 | 3 | LOW | Compliance Lead | Q4 2025 | Process Defined
SUMMARY | [5 empty] | 13.7 | Average Residual Score → |  |  | 5.9 | Review cadence: Quarterly (High) ¦ Bi-annually (Medium/Low)

## Heat Map
RISK HEAT MAP — BrightPay Fintech
ISO 27001:2022 Annex A ¦ 5×5 Likelihood × Impact Matrix ¦ 2025
IMPACT →
| 1 — Negligible | 2 — Minor | 3 — Moderate | 4 — Major | 5 — Catastrophic
5 — Almost Certain | Score: 5 | Score: 10 | Score: 15 | Score: 20 | Score: 25
4 — Likely | Score: 4 | Score: 8 | Score: 12 R-006 | Score: 16 R-004 | Score: 20 R-001
3 — Possible | Score: 3 | Score: 6 | Score: 9 | Score: 12 R-003 R-005 R-009 | Score: 15 R-002 R-007 R-008
2 — Unlikely | Score: 2 | Score: 4 | Score: 6 | Score: 8 R-010 | Score: 10
1 — Rare | Score: 1 | Score: 2 | Score: 3 | Score: 4 | Score: 5
RISK TIER LEGEND
CRITICAL (Score 20–25) |  | Immediate escalation to CISO ¦ P1 Response SLA
HIGH (Score 15–19) |  | Immediate controls required ¦ Quarterly review
MEDIUM (Score 8–14) |  | Controls required ¦ Bi-annual review
LOW-MEDIUM (Score 5–7) |  | Monitor ¦ Annual review
LOW (Score 1–4) |  | Accept with monitoring ¦ Annual review
RESIDUAL RISK HEAT MAP (After Controls Applied)
IMPACT →
| 1 — Negligible | 2 — Minor | 3 — Moderate | 4 — Major | 5 — Catastrophic
5 — Almost Certain | Score: 5 | Score: 10 | Score: 15 | Score: 20 | Score: 25
4 — Likely | Score: 4 | Score: 8 | Score: 12 | Score: 16 | Score: 20
3 — Possible | Score: 3 | Score: 6 | Score: 9 | Score: 12 | Score: 15
2 — Unlikely | Score: 2 | Score: 4 | Score: 6 R-002 R-003 R-006 R-009 | Score: 8 R-001 R-004 R-005 | Score: 10
1 — Rare | Score: 1 | Score: 2 | Score: 3 R-010 | Score: 4 R-007 R-008 | Score: 5

## Control Mapping
ISO 27001:2022 Annex A — Control Mapping
Risk ID | Annex A Control | Control Description | Control Type | Implementation Status | Effectiveness | Annex A Ref
R-001 | Multi-Factor Authentication | Enforce MFA for all API access and admin logins to prevent credential-based attacks | Preventive | Implemented | High | A.8.5
R-001 | Role-Based Access Control | Restrict API and system access to authorised roles only; review quarterly | Preventive | Implemented | High | A.8.2
R-002 | Encryption at Rest | AES-256 encryption applied to all customer PII and payment data in storage | Preventive | Implemented | High | A.8.24
R-003 | Access Review | Quarterly review of all privileged account access rights to detect unnecessary privileges | Detective | Implemented | Medium | A.8.3
R-004 | Web Application Firewall | WAF deployed to filter malicious traffic and DDoS attempts on payment gateway | Preventive | Implemented | High | A.8.20
R-004 | Rate Limiting | API rate limiting to throttle excessive requests and prevent DDoS amplification | Preventive | Implemented | Medium | A.8.20
R-005 | Supplier Information Security Policy | Vendor risk assessments and contractual security requirements for all third-party APIs | Preventive | Implemented | Medium | A.5.19
R-006 | Malware Protection | Endpoint Detection and Response (EDR) deployed across all employee endpoints | Detective | Implemented | High | A.8.7
R-006 | Security Awareness Training | Annual phishing simulation and security awareness training for all staff | Preventive | Implemented | Medium | A.6.3
R-007 | Secure Configuration Management | Cloud security posture management (CSPM) with automated misconfiguration alerts | Detective | Implemented | High | A.8.9
R-008 | Application Security Testing | Regular penetration testing and vulnerability assessments of web applications | Corrective | Scheduled | High | A.8.8
R-009 | Password and Credential Policy | Privileged access management (PAM) with enforced rotation and complexity policies | Preventive | Implemented | High | A.8.5
R-010 | Supplier Relationship Management | Structured vendor onboarding process including security questionnaire and SoA review | Preventive | Implemented | Medium | A.5.19